## Testing Road Map
Team 3 - Testing Scope
|  | Test Cycle 1 | Test Cycle 2 | Test Cycle 3
Xero Application Modules | Feature Backlog | Cycle 1 - 11/22/24 | Cycle 2 - 12/06/24 | Cycle 3 - 12/13/24
01. Dashboard
02. User Management and Authentication
03. Settings and Configuration
04. Financial Data Entry
05. Bank Feeds and Reconciliations
06. Invoicing
07. Accounts Receivable
08. Purchase Orders | 8.01 Create Order | X
| 8.02 Edit Purchase Order | X
| 8.03 Delete Purchase Order | X
| 8.04 Approve Purchase Order | X
| 8.05 Send Purchase Order | X
| 8.06 Viewving and Managing Purchase Order | X
| 8.07 Order Acknowledgement | X
| 8.08 Tracking Order Delivery | X
| 8.09 Receipt of Services | X
| 8.10 3-way Marching | X
| 8.11 Invoice processing & Payment | X
| 8.12 Close Purchase Order | X
| 8.13 Audit Trail Process | X
| 8.14 Supplier Management | X
| 8.15 Spend Dashboard | X
| 8.16 Multi-Currency support | X
09. Expense Claims | 9.01 Add Claims |  | x
| 9.02 Add a new Expense claim |  | x
| 9.03 Add comments to Expense Claims |  | x
| 9.04 Assign Expense Claim Category |  | x
| 9.05 Submit expense claim |  | x
| 9.06 Approve Expense Claim |  | x
| 9.07 Reject Expense Claim |  | x
| 9.08 Mark as paid on Expense claim |  | x
| 9.09 Paying the claim |  | x
| 9.10 Process Reimbursement |  | x
| 9.11 Get Claim History |  | x
| 9.12 Delete ExpenseClaim |  | x
| 9.13 Edit Expense Claims |  | x
10. Bills to Pay
11. Accounts Payable | 11.01 Add the Contact of the Shipper |  |  | x
| 11.02 Edit the existing contact of the shipper |  |  | x
| 11.03 Archive inactive cntacts |  |  | x
| 11.04 Search or filter the contact |  |  | x
| 11.05 Receiving the invoice |  |  | x
| 11.06 Sorting the invoice according to date |  |  | x
| 11.07 Verifying the invoice |  |  | x
| 11.08 Approval of the invoice |  |  | x
| 11.09 Enter the bills into the system |  |  | x
| 11.10 Track and manage the Bills |  |  | x
| 11.11 Sort the bills |  |  | x
| 11.12 Pay the Bills |  |  | x
| 11.13 Record the Payment |  |  | x
| 11.14 Report the Payment |  |  | x
12. Accounting Reports